## Project Planner
Accident Analysis Software
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 5 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (DAYS)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Planning | 1 | 7 | 1 | 7 | 100%
1.1 Meeting with Team Members | 1 | 1 | 1 | 1 | 100%
1.2 Understanding Project Requirements | 1 | 1 | 1 | 1 | 100%
1.3 Github Repository Configuration | 2 | 1 | 2 | 1 | 100%
1.4 Project Scheduling | 3 | 5 | 3 | 5 | 100%
2. Analysis | 8 | 14 |  |  | 0%
2.1 Project Background Information | 8 | 2 | 8 | 1 | 0%
2.2 Define System Vision | 8 | 2 | 8 | 1 | 0% | bar: PERIODS (DAYS) 10
2.3 Define Activities & Estimations | 10 | 2 | 8 | 10 | 100% | bar: PERIODS (DAYS) 12
2.4 Define System Functions | 12 | 2 | 15 | 1 | 0% | bar: PERIODS (DAYS) 14; PERIODS (DAYS) 16
2.5 Define User & Software Requirements | 14 | 8 | 14 | 21 | 0%
2.6 Define & Analyse Use Cases | 15 | 1 | 21 |  | 0%
2.7 Gantt Chart & Work Breakdown Structure | 15 | 3 | 8 | 10 | 0%
3. Design | 15 | 20 | 15 |  | 0% | bar: PERIODS (DAYS) 36; PERIODS (DAYS) 40; PERIODS (DAYS) 42
3.1 Software Design Plan | 21 | 7 | 21 |  | 0% | bar: PERIODS (DAYS) 36; PERIODS (DAYS) 40; PERIODS (DAYS) 42
3.2 User Interface Design Plan | 15 | 7 | 15 | 7 | 100% | bar: PERIODS (DAYS) 34; PERIODS (DAYS) 36; PERIODS (DAYS) 38; PERIODS (DAYS) 40; PERIODS (DAYS) 42
3.3 Define Data Structures | 21 | 7 | 21 |  | 30% | bar: PERIODS (DAYS) 36; PERIODS (DAYS) 38; PERIODS (DAYS) 40; PERIODS (DAYS) 42; PERIODS (DAYS) 46
3.4 Wireframes | 15 | 7 | 15 | 7 | 100% | bar: PERIODS (DAYS) 36; PERIODS (DAYS) 38; PERIODS (DAYS) 40; PERIODS (DAYS) 42; PERIODS (DAYS) 46
3.5 Mock-up Design | 14 | 5 | 15 | 7 | 100% | bar: PERIODS (DAYS) 36; PERIODS (DAYS) 38; PERIODS (DAYS) 40; PERIODS (DAYS) 42
3.6 Graphics & Assets | 15 | 7 | 15 | 7 | 100%
3.7 Structural Design | 15 | 7 | 15 | 7 | 100%
3.8 System Detailed Design | 15 | 7 | 15 | 7 | 100%
4. Devlopment | 21 | 21 |  |  | 0%
4.1 Required Feature 1 | 21 | 7 |  |  | 0%
4.2 Required Feature 2 | 21 | 7 |  |  | 0%
4.3 Required Feature 3 | 21 | 7 |  |  | 0%
4.4 Required Feature 4 | 28 | 14 |  |  | 0%
4.5 Required Feature 5 | 28 | 14 |  |  | 0%
5. Testing | 42 | 12 |  |  | 0%
5.1 Unit Tests | 42 | 4 |  |  | 0%
5.2 Coverage Report | 45 | 4 |  |  | 0%
5.3 Requirements Acceptance Testing | 48 | 4 |  |  | 0%
6.0 Administration | 55 | 6 |  |  | 0%
6.1 Executive Summary | 55 | 6 |  |  | 0%
6.2 Update Work Breakdown Structure & Gantt Chart | 55 | 6 |  |  | 0%
6.3 Update Design Document | 55 | 6
6.4 Instruction User Manual | 55 | 6 |  |  | 0%