## Project Planner
Accident Analysis Software
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Conceptualise | 1 | 5 |  |  | 0%
1.1 Understanding Project Requirements |  |  |  |  | 0%
1.2 Outcomes of the Project |  |  |  |  | 0%
1.3 Dataset Decision |  |  |  |  | 0%
1.4 Expectations |  |  |  |  | 0%
1.5 Github Repository Configuration |  |  |  |  | 0%
1.6 Research |  |  |  |  | 0%
1.7 Git & Github Training |  |  |  |  | 0%
2. Planning |  |  |  |  | 0%
2.1 Work Breakdown Structure |  |  |  |  | 0%
2.2 Gantt Chart |  |  |  |  | 0%
2.3 Project Plan Introduction |  |  |  |  | 0%
2.4 Activity Definition & Estimation |  |  |  |  | 0%
2.5 System Vision & Requirements |  |  |  |  | 0%
2.6 Software and User Interface Design Plan |  |  |  |  | 0%
2.7 Part A Submission |  |  |  |  | 0%
3. Devlopment |  |  |  |  | 0%
3.1 Required Feature 1 |  |  |  |  | 0%
3.2 Required Feature 2 |  |  |  |  | 0%
3.3 Required Feature 3 |  |  |  |  | 0%
3.4 Required Feature 4 |  |  |  |  | 0%
3.5 Required Feature 5 |  |  |  |  | 0%
3.6 Software Design |  |  |  |  | 0%
3.7 User Interface Design |  |  |  |  | 0%
4. Final Prep |  |  |  |  | 0%
4.1 Testing Plan |  |  |  |  | 0%
4.2 Unit Tests & Coverage Test Results |  |  |  |  | 0%
4.3 Update Project Plan |  |  |  |  | 0%
4.4 Update System Design Document |  |  |  |  | 0%
4.5 Update Gantt Chart |  |  |  |  | 0%
4.6 Executive Summary |  |  |  |  | 0%
4.7 Instruction Booklet/User Manual |  |  |  |  | 0%
5. Release |  |  |  |  | 0%
5.1 Software Release |  |  |  |  | 0%
5.2 Release Analysis |  |  |  |  | 0%
5.3 Necessary Updates |  |  |  |  | 0%
5.4 Support |  |  |  |  | 0%
5.5 Final Check & Consolidation |  |  |  |  | 0%
5.6 Part B Submission |  |  |  |  | 0%
5.7 Reflection |  |  |  |  | 0%